## Mobily billing actuals
SNO | Resource | Date onboarded | Task ID | Estimator Points | Current Milestone | Invoicing calendar | Invoice | Comments | Invoice due | Earned SP (basis approved TS till Apr '26) | Billed SP (basis dump shared till Apr'26) | Balance SP to invoice (earned - billed) (as on Apr '26) | Unbilled (INR) | unbilled points as per mobily dump till Apr '26 | Unbilled Amount as per mobily dump till Apr '26 (INR) |  | Employee Name | Billing rate | Jan '26 | Feb '26 | Mar '26 | Apr '26 | May '26 | Jun '26 | Jul '26 | Aug '26 | Sep '26 | Oct '26 | Nov '26 | Dec '26 | Total
1 | Rajender Mukunda | 2021-02-23 | AE-15831 | 26 | RFS | 15.6 | 163035.6 | UAT - Oct '25 | Oct '25 | 137.15 | 152.94 | -15.79 | -165021.29 | 7.28 | 76083.28 | 1.3 | Rajendra Mukunda | 10451 | 13 | 20 | 19 | 14 | 18 | 21.5 | [6 empty] | 105.5
[6 empty] | 5.2 | 54345.2 | RFS -Nov '25 | Dec '25
[6 empty] | 5.2 | 54345.2 | PAC - Jan '26 | Feb '26
|  |  | AE-16073 | 26 | RFS | 15.6 | 163035.6 | UAT - Nov '25 | Nov '25
[6 empty] | 5.2 | 54345.2 | RFS - Dec '25 | Dec '25
[6 empty] | 5.2 | 54345.2 | PAC - Feb '26 | Feb '26
|  |  | AE-16451 | 24.5 | UAT | 14.7 | 153629.7 | UAT - Dec '25 | Dec '25
[6 empty] | 4.9 | 51209.9 | RFS - Dec '25 | Dec '25
[6 empty] | 4.9 | 51209.9 | PAC - Feb '26 | Feb '26
|  |  | AE-16452 | 23.66 | RFS | 14.196 | 148362.396 | UAT - Jan '26 | Jan '26
[6 empty] | 4.732 | 49454.132 | RFS - Jan '26 | Jan '26
[6 empty] | 4.732 | 49454.132 | PAC - Mar '26 | Mar '26
|  |  | AE-16641 | 36.4 | UAT | 21.84 | 228249.84 | UAT - Feb '26 | Feb '26
[6 empty] | 7.28 | 76083.28 | RFS - Mar '26 | May '26
[6 empty] | 7.28 | 76083.28 | PAC - Apr '26 | Apr '26
|  |  | AE-16642 | 24.7 | RFS | 14.82 | 154883.82 | UAT - Apr '26 | Apr '26
[6 empty] | 4.94 | 51627.94 | RFS - Apr '26 | Apr '26
[6 empty] | 4.94 | 51627.94 | PAC - Jun '26 | Jun '26
|  |  | AE-16887 | 19.6 | RFS | 11.76 | 122903.76 | UAT - Apr '26 | Apr '26
[6 empty] | 3.92 | 40967.92 | RFS - Apr '26 | Apr '26
[6 empty] | 3.92 | 40967.92 | PAC - Jun '26 | Jun '26
|  |  | AE-16910 | 23.4 | UAT | 14.04 | 146732.04 | UAT - May '26 | May '26
[6 empty] | 4.68 | 48910.68 | RFS - May '26 | May '26
[6 empty] | 4.68 | 48910.68 | PAC - Jul '26 | Jul '26
|  |  | AE-17040 | 27.3 | UAT | 16.38 | 171187.38 | UAT - Jun '26 | Jun '26
[6 empty] | 5.46 | 57062.46 | RFS - Jun '26 | Jun '26
[6 empty] | 5.46 | 57062.46 | PAC - Aug '26 | Aug '26
[5 empty] | UAT | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[5 empty] | UAT | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[10 empty] | 137.15 | 152.94 | -15.79 | -165021.29 | 7.28 | 76083.28
invoiced
uninvoiced
Note on V29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mobily 16, as first few day access card was not there. Mail in progress but followup need to be expedited